## Shopenzer Testcases
|  |  |  | Date | 2022-11-03
|  |  |  | Team ID | PNT2022TMID36050
|  |  |  | Project Name | Project - Exploratory Analysis of RainFall Data in India for Agriculture
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
Home_page_T1 | Functional | Home Page | Verify if user is able to see the contents of the prediction page/home page when user clicks on the flask app URL | - | 1.Click the flask app URL 2.The contents are readily available for the user to read | - | All precautions should get displayed | Working as expected | Pass | The home page opens when the URL is clicked |  |  | Aruna P
Home_page_T2 | UI | Home Page | Verify all the UI elements in home page | - | 1.Click the flask app URL 2.The contents are readily available for the user to read | - | All precautions should get displayed | The page is properly displayed | Pass | All the components of the web page are displayed correctly |  |  | Anurag Manoj Badge
Home_page_T3 | Functional | Home page | Verify if user is able to navigate to the Predictor page from the home page | - | 1. Click the flask app URL 2. Click on the predictor tab to open the predictor input page | - | The predictor input page should get opened | Working as expected | Pass | The predictor input page was opened |  |  | Nethra Janardhanan
Home_page_T4 | Functional | Home page | Verify if user is able to navigate to the Trend Analysis page from the home page | - | 1. Click the flask app URL 2. Click on the Trend Analysis tab to open the Trend Analysis input page | - | The trend analysis input page should get opened | Working as expected | Pass | The trend analysis input page was opened |  |  | Anurag Manoj Badge
Predictor_page_T1 | UI | Predictor Input page | Verify all the UI elements in predictor input page |  | 1. Click the flask app URL 2. Click the predictor tab on the home page | - | All the input boxes from the predictor input page should be be displayed correctly. All the css included. | The page is properly displayed | Pass | All the input boxes are properly aligned, the background picture is also clearly visible. |  |  | Aruna P
Predictor_page_T2 | Functional | Predictor Input page | Navigate from this page to all pages |  | 1. Click the flask app URL 2. Click the predictor tab on the home page 3. Click the home tab on the predictor page 4. Click the predictor tab to come back 5. Click the trend analysis tab on the predictor page | - | The connections are all accurate and the requested web pages are displayed correctly | Working as expected | Pass | All input pages are displayed correctly |  |  | Nethra Janardhanan, Astha Shrivastava
Predictor_page_T3 | Functional | Predictor | Give all inputs to test for accurate prediction |  | 1. Click the flask app URL 2. Click the predictor tab on the home page 3. Enter all the input values and hit enter | [13.4, 22.9, 0.6, 0.2, 0.4, 44.0, 20.0, 24.0, 71.0, 22.0, 1007.7, 1007.1, 8, 16.9, 21.8, 21.8] | The correct prediction should get displayed. i.e., Prediction: RainFall tomorrow: No | Working as expected | Pass | The predictor is working |  |  | Vihitha Kota, Aruna P
Predictor_page_T4 | UI | Predictor Output page | Verify all the UI elements in predictor output page |  | 1. Click the flask app URL 2. Click the predictor tab on the home page 3. Enter all the input values and hit enter | - | The output obtained from the predictor or the deployed model shoud be correctly displayed. | The output is displayed | Pass | The output is displayed |  |  | Vihitha Kota
Trend_Analysis_page_T1 | UI | Trend Analysis Input page | Verify all the UI elements in Trend analysis input page |  | 1. Click the flask app URL 2. Click the Trend analysis tab on the home page | - | All the input boxes from the trend analysis input page should be be displayed correctly. All the css included. | The page is properly displayed | Pass | All the input boxes are properly aligned, the background picture is also clearly visible. |  |  | Astha Shrivastava
Trend_Analysis_page_T2 | Functional | Trend Analysis Input page | Navigate from this page to all pages |  | 1. Click the flask app URL 2. Click the Trend Analysis tab on the home page 3. Click the home tab on the Trend Analysis page 4. Click the Trend Analysis tab to come back 5. Click the predictor tab on the Trend Analysis page | - | The connections are all accurate and the requested web pages are displayed correctly | Working as expected | Pass | All input pages are displayed correctly |  |  | Anurag Manoj Badge
Trend_Analysis_page_T3 | Functional | Trend Analysis | Give all inputs to test for accurate output |  | 1. Click the flask app URL 2. Click the trend analysis tab on the home page 3. Enter all the input values and hit enter | Place: Uluru Year: 2010 | The correct processed output should get displayed. i.e., the table containing the information requested by user is displayed. | Working as expected | Pass | The trend analyzer is working |  |  | Nethra Janardhanan, Astha Shrivastava
Trend_Analysis_page_T4 | UI | Trend Analysis Output page | Verify all the UI elements in Trend Analysis output page |  | 1. Click the flask app URL 2. Click the trend analysis tab on the home page 3. Enter all the input values and hit enter | - | The output obtained from the python code for processing and returning the required output shoud be correctly displayed. | The output is displayed | Pass | The output is displayed |  |  | Vihitha Kota, Aruna P

## Testscearnios
Test Scenarios
1 | Verify user is able to see login page
2 | Verify user is able to loginto application or not?
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to recovery password
5 | Veriify login page elements
Search
1 | Verify user is able to search by entering keywords in search box
2 | Verify user is able to see suggestions based on keyword entered in search box
3 | Verify user is able to see related auto suggestions displaying based on keyword entered in search box
4 | Verify user is able to see no matches found message when no results are matching with entered keyword
5 | Verify user is able to see seach detailed page when nothing entered in textbox